## 项目信息
项目名称 | APS 上线实施示例
项目经理 | 王敏
项目开始 | 2026-07-01
备注 | 内置示例。改表格或拖甘特条，计划和风险会一起变。
按前置推期 | 否
客户 | 示例工厂
版本 | MVP

## 阶段
id | 阶段 | 顺序
p1 | 启动 | 1
p2 | 实施 | 2
p3 | 上线收尾 | 3

## WBS
id | parentId | WBS | 任务名称 | 阶段 | 负责人 | 开始 | 结束 | 工期 | 进度 | 前置 | 状态 | 交付物
1 |  | 1 | 启动 | 启动 | 王敏 | 2026-07-01 | 2026-07-17 | 17 | 58 |  | 进行中 | 启动包
2 | 1 | 1.1 | 立项与范围 | 启动 | 王敏 | 2026-07-01 | 2026-07-07 | 7 | 100 |  | 已完成 | 范围说明书
3 | 1 | 1.2 | 干系人确认 | 启动 | 李强 | 2026-07-08 | 2026-07-12 | 5 | 60 | 1.1 | 进行中 | 干系人清单
4 | 1 | 1.3 | 环境与账号 | 启动 | 赵磊 | 2026-07-10 | 2026-07-17 | 8 | 20 | 1.2 | 进行中
5 |  | 2 | 实施 | 实施 | 陈洁 | 2026-07-20 | 2026-09-18 | 61 | 6 |  | 进行中 | 实施包
6 | 5 | 2.1 | 主数据准备 | 实施 | 陈洁 | 2026-07-20 | 2026-07-30 | 11 | 32 | 1.3 | 进行中 | 物料主数据
7 | 6 | 2.1.1 | 物料编码清洗 | 实施 | 周宁 | 2026-07-20 | 2026-07-25 | 6 | 50 |  | 进行中
8 | 6 | 2.1.2 | BOM 核对 | 实施 | 周宁 | 2026-07-26 | 2026-07-30 | 5 | 10 | 2.1.1 | 进行中
9 | 5 | 2.2 | 工艺路线 | 实施 | 孙悦 | 2026-08-01 | 2026-08-08 | 8 | 0 | 2.1.2 | 未开始 | 工艺路线表
10 | 5 | 2.3 | 排程规则 | 实施 | 孙悦 | 2026-08-10 | 2026-08-16 | 7 | 0 | 2.2 | 未开始 | 规则清单
11 | 5 | 2.4 | 联调与试跑 | 实施 | 陈洁 | 2026-08-01 | 2026-09-18 | 49 | 2 | 2.3 | 未开始
16 | 11 | 2.4.1 | 试跑场景 1 | 实施 |  | 2026-08-01 | 2026-08-02 | 2 | 15 |  | 进行中 | 场景说明 1
17 | 11 | 2.4.2 | 试跑场景 2 | 实施 | 孙悦 | 2026-08-03 | 2026-08-05 | 3 | 15 |  | 进行中
18 | 11 | 2.4.3 | 试跑场景 3 | 实施 | 陈洁 | 2026-08-05 | 2026-08-08 | 4 | 15 |  | 进行中
19 | 11 | 2.4.4 | 试跑场景 4 | 实施 | 赵磊 | 2026-08-07 | 2026-08-08 | 2 | 15 |  | 进行中
20 | 11 | 2.4.5 | 试跑场景 5 | 实施 | 周宁 | 2026-08-09 | 2026-08-11 | 3 | 0 |  | 未开始
21 | 11 | 2.4.6 | 试跑场景 6 | 实施 |  | 2026-08-11 | 2026-08-14 | 4 | 0 |  | 未开始
22 | 11 | 2.4.7 | 试跑场景 7 | 实施 | 陈洁 | 2026-08-02 | 2026-08-03 | 2 | 0 |  | 未开始
23 | 11 | 2.4.8 | 试跑场景 8 | 实施 | 赵磊 | 2026-08-04 | 2026-08-06 | 3 | 0 |  | 未开始 | 场景说明 8
24 | 11 | 2.4.9 | 试跑场景 9 | 实施 | 周宁 | 2026-08-06 | 2026-08-09 | 4 | 0 |  | 未开始
25 | 11 | 2.4.10 | 试跑场景 10 | 实施 | 孙悦 | 2026-08-08 | 2026-08-09 | 2 | 0 |  | 未开始
26 | 11 | 2.4.11 | 试跑场景 11 | 实施 |  | 2026-08-10 | 2026-08-12 | 3 | 0 |  | 未开始
27 | 11 | 2.4.12 | 试跑场景 12 | 实施 | 赵磊 | 2026-08-12 | 2026-08-15 | 4 | 0 |  | 未开始
28 | 11 | 2.4.13 | 试跑场景 13 | 实施 | 周宁 | 2026-08-03 | 2026-08-04 | 2 | 0 |  | 未开始
29 | 11 | 2.4.14 | 试跑场景 14 | 实施 | 孙悦 | 2026-08-05 | 2026-08-07 | 3 | 0 |  | 未开始
30 | 11 | 2.4.15 | 试跑场景 15 | 实施 | 陈洁 | 2026-08-07 | 2026-08-10 | 4 | 0 |  | 未开始 | 场景说明 15
31 | 11 | 2.4.16 | 试跑场景 16 | 实施 |  | 2026-08-09 | 2026-08-10 | 2 | 0 |  | 未开始
32 | 11 | 2.4.17 | 试跑场景 17 | 实施 | 周宁 | 2026-08-11 | 2026-08-13 | 3 | 0 |  | 未开始
33 | 11 | 2.4.18 | 试跑场景 18 | 实施 | 孙悦 | 2026-08-13 | 2026-08-16 | 4 | 0 |  | 未开始
34 | 11 | 2.4.19 | 试跑场景 19 | 实施 | 陈洁 | 2026-09-04 | 2026-09-05 | 2 | 0 |  | 未开始
35 | 11 | 2.4.20 | 试跑场景 20 | 实施 | 赵磊 | 2026-09-06 | 2026-09-08 | 3 | 0 |  | 未开始
36 | 11 | 2.4.21 | 试跑场景 21 | 实施 |  | 2026-09-08 | 2026-09-11 | 4 | 0 |  | 未开始
37 | 11 | 2.4.22 | 试跑场景 22 | 实施 | 孙悦 | 2026-09-10 | 2026-09-11 | 2 | 0 |  | 未开始 | 场景说明 22
38 | 11 | 2.4.23 | 试跑场景 23 | 实施 | 陈洁 | 2026-09-12 | 2026-09-14 | 3 | 0 |  | 未开始
39 | 11 | 2.4.24 | 试跑场景 24 | 实施 | 赵磊 | 2026-09-14 | 2026-09-17 | 4 | 0 |  | 未开始
40 | 11 | 2.4.25 | 试跑场景 25 | 实施 | 周宁 | 2026-09-05 | 2026-09-06 | 2 | 0 |  | 未开始
41 | 11 | 2.4.26 | 试跑场景 26 | 实施 |  | 2026-09-07 | 2026-09-09 | 3 | 0 |  | 未开始
42 | 11 | 2.4.27 | 试跑场景 27 | 实施 | 陈洁 | 2026-09-09 | 2026-09-12 | 4 | 0 |  | 未开始
43 | 11 | 2.4.28 | 试跑场景 28 | 实施 | 赵磊 | 2026-09-11 | 2026-09-12 | 2 | 0 |  | 未开始
44 | 11 | 2.4.29 | 试跑场景 29 | 实施 | 周宁 | 2026-09-13 | 2026-09-15 | 3 | 0 |  | 未开始 | 场景说明 29
45 | 11 | 2.4.30 | 试跑场景 30 | 实施 | 孙悦 | 2026-09-15 | 2026-09-18 | 4 | 0 |  | 未开始
12 |  | 3 | 上线收尾 | 上线收尾 | 王敏 | 2026-09-01 | 2026-09-21 | 21 | 0 |  | 未开始 | 上线报告
13 | 12 | 3.1 | 培训 | 上线收尾 | 李强 | 2026-09-01 | 2026-09-05 | 5 | 0 | 2.4 | 未开始 | 培训记录
14 | 12 | 3.2 | 切换窗口 | 上线收尾 | 赵磊 | 2026-09-08 | 2026-09-10 | 3 | 0 | 3.1 | 未开始
15 | 12 | 3.3 | 稳定观察 | 上线收尾 | 陈洁 | 2026-09-12 | 2026-09-21 | 10 | 0 | 3.2 | 未开始

## 依赖
id | 前置任务 | 后置任务 | 类型
d1 | 2 | 3 | FS
d2 | 3 | 4 | FS
d3 | 4 | 6 | FS
d4 | 7 | 8 | FS
d5 | 8 | 9 | FS
d6 | 9 | 10 | FS
d7 | 10 | 11 | FS
d8 | 11 | 13 | FS
d9 | 13 | 14 | FS
d10 | 14 | 15 | FS

## 风险规则
id | 名称 | 类型 | 启用 | 严重度 | 范围 | 阶段 | 参数JSON
r1 | 任务名称必填 | missing_field | 是 | high | all |  | {"field":"name"}
r2 | 负责人必填 | missing_field | 是 | medium | leaves |  | {"field":"owner"}
r3 | 结束早于开始 | date_inverted | 是 | high | all |  | {}
r4 | 已过期未完成 | overdue | 是 | high | leaves |  | {"progressBelow":100}
r5 | 进行中进度偏低 | stale_progress | 是 | medium | leaves |  | {"progressBelow":30,"status":"进行中"}
r6 | 前置任务重叠 | predecessor_overlap | 是 | high | leaves |  | {}
r7 | 父任务未覆盖子任务 | parent_not_covering | 是 | medium | all |  | {}
r8 | 工期与起止不一致 | duration_mismatch | 是 | low | leaves |  | {"toleranceDays":0}
r9 | 工期超过 20 天 | threshold | 是 | low | leaves |  | {"field":"duration","op":">","value":20}

## 风险结果
id | 规则 | 任务 | WBS | 严重度 | 说明
r2:16 | 负责人必填 | 试跑场景 1 | 2.4.1 | medium | 2.4.1 缺少「负责人」
r2:21 | 负责人必填 | 试跑场景 6 | 2.4.6 | medium | 2.4.6 缺少「负责人」
r2:26 | 负责人必填 | 试跑场景 11 | 2.4.11 | medium | 2.4.11 缺少「负责人」
r2:31 | 负责人必填 | 试跑场景 16 | 2.4.16 | medium | 2.4.16 缺少「负责人」
r2:36 | 负责人必填 | 试跑场景 21 | 2.4.21 | medium | 2.4.21 缺少「负责人」
r2:41 | 负责人必填 | 试跑场景 26 | 2.4.26 | medium | 2.4.26 缺少「负责人」
r4:3 | 已过期未完成 | 干系人确认 | 1.2 | high | 1.2 已过结束日且进度 60% < 100%
r4:4 | 已过期未完成 | 环境与账号 | 1.3 | high | 1.3 已过结束日且进度 20% < 100%
r4:7 | 已过期未完成 | 物料编码清洗 | 2.1.1 | high | 2.1.1 已过结束日且进度 50% < 100%
r4:8 | 已过期未完成 | BOM 核对 | 2.1.2 | high | 2.1.2 已过结束日且进度 10% < 100%
r4:9 | 已过期未完成 | 工艺路线 | 2.2 | high | 2.2 已过结束日且进度 0% < 100%
r4:10 | 已过期未完成 | 排程规则 | 2.3 | high | 2.3 已过结束日且进度 0% < 100%
r4:16 | 已过期未完成 | 试跑场景 1 | 2.4.1 | high | 2.4.1 已过结束日且进度 15% < 100%
r4:17 | 已过期未完成 | 试跑场景 2 | 2.4.2 | high | 2.4.2 已过结束日且进度 15% < 100%
r4:18 | 已过期未完成 | 试跑场景 3 | 2.4.3 | high | 2.4.3 已过结束日且进度 15% < 100%
r4:19 | 已过期未完成 | 试跑场景 4 | 2.4.4 | high | 2.4.4 已过结束日且进度 15% < 100%
r4:20 | 已过期未完成 | 试跑场景 5 | 2.4.5 | high | 2.4.5 已过结束日且进度 0% < 100%
r4:21 | 已过期未完成 | 试跑场景 6 | 2.4.6 | high | 2.4.6 已过结束日且进度 0% < 100%
r4:22 | 已过期未完成 | 试跑场景 7 | 2.4.7 | high | 2.4.7 已过结束日且进度 0% < 100%
r4:23 | 已过期未完成 | 试跑场景 8 | 2.4.8 | high | 2.4.8 已过结束日且进度 0% < 100%
r4:24 | 已过期未完成 | 试跑场景 9 | 2.4.9 | high | 2.4.9 已过结束日且进度 0% < 100%
r4:25 | 已过期未完成 | 试跑场景 10 | 2.4.10 | high | 2.4.10 已过结束日且进度 0% < 100%
r4:26 | 已过期未完成 | 试跑场景 11 | 2.4.11 | high | 2.4.11 已过结束日且进度 0% < 100%
r4:27 | 已过期未完成 | 试跑场景 12 | 2.4.12 | high | 2.4.12 已过结束日且进度 0% < 100%
r4:28 | 已过期未完成 | 试跑场景 13 | 2.4.13 | high | 2.4.13 已过结束日且进度 0% < 100%
r4:29 | 已过期未完成 | 试跑场景 14 | 2.4.14 | high | 2.4.14 已过结束日且进度 0% < 100%
r4:30 | 已过期未完成 | 试跑场景 15 | 2.4.15 | high | 2.4.15 已过结束日且进度 0% < 100%
r4:31 | 已过期未完成 | 试跑场景 16 | 2.4.16 | high | 2.4.16 已过结束日且进度 0% < 100%
r4:32 | 已过期未完成 | 试跑场景 17 | 2.4.17 | high | 2.4.17 已过结束日且进度 0% < 100%
r4:33 | 已过期未完成 | 试跑场景 18 | 2.4.18 | high | 2.4.18 已过结束日且进度 0% < 100%
r5:4 | 进行中进度偏低 | 环境与账号 | 1.3 | medium | 1.3 状态为进行中但进度仅 20%
r5:8 | 进行中进度偏低 | BOM 核对 | 2.1.2 | medium | 2.1.2 状态为进行中但进度仅 10%
r5:16 | 进行中进度偏低 | 试跑场景 1 | 2.4.1 | medium | 2.4.1 状态为进行中但进度仅 15%
r5:17 | 进行中进度偏低 | 试跑场景 2 | 2.4.2 | medium | 2.4.2 状态为进行中但进度仅 15%
r5:18 | 进行中进度偏低 | 试跑场景 3 | 2.4.3 | medium | 2.4.3 状态为进行中但进度仅 15%
r5:19 | 进行中进度偏低 | 试跑场景 4 | 2.4.4 | medium | 2.4.4 状态为进行中但进度仅 15%
r6:4 | 前置任务重叠 | 环境与账号 | 1.3 | high | 1.3 开始于 2026-07-10，早于或等于前置 1.2 的结束 2026-07-12
r6:13 | 前置任务重叠 | 培训 | 3.1 | high | 3.1 开始于 2026-09-01，早于或等于前置 2.4 的结束 2026-09-18